## W46.2
working type | Content | time | status | comments/issues
New poc
| silot | 3hours | done | AER已寄出，等待客户测试
O&M tasks | xiongdi | 30min | done | online 对接
O&M backlog | haproxy anos test | 5hours | ongoing | 1c1g ongoing
O&M operation record | Content | operator
xiongdi | change DNS server | TM
huami | change grafana name | TM

## W46.3
working type | Content | time | status | comments/issues
New poc
O&M tasks | zhaoxin | 1.5hour | ongoing | 北京下行流量小，经测试怀疑是客户isp丢包引起，待客户检查
O&M backlog | aws bj-nx | 5min | done | 2 weeks peer test finished, no outstanding failure/packet loss
| haproxy-test | 6.5hours | ongoing | 1c1g almost done, 2c2g test tomorrow
O&M operation record | mbyte | 5min | done | QoS未生效，重新设置

## W46.4
working type | Content | time | status | comments/issues
New poc
O&M tasks
O&M backlog
O&M operation record | Content | operator

## W46.5
working type | Content | time | status | comments/issues
New poc
O&M Task
O&M backlog
O&M operation record | Content | operator