## w02.1
working type | Content | time | status | comments/issues
New poc
O&M tasks
O&M backlog | new avr regression test | 6 hours | ongoing | 需重打stability，开始IRT测试
alert learning
all time |  | 9hours
O&M operation record | Content | operator
ISmarket | 加北京和美国的三方监控 | TM
Daziran | 修改alert邮件丢包阈值 | TM
Quanshi | deletion盒子归档 | TM

## W02.2
working type | Content | time | status | comments/issues
New poc | quanshi | 1hour | ongoing | 协商细节，等前端协商技术细节
O&M tasks
O&M backlog | new avr 1.2.3 test | 3hours | ongoing | big i3 test ongoing
| alert learning | 5hours | ongoing | 根据客户拓扑查看consul是否有遗漏，学习客户拓扑
all time
O&M operation record | Content | operator
qinghe | prod | TM

## W02.3
working type | Content | time | status | comments/issues
New poc | quanshi | 5hours | finished | 确认inline mode,测试可用并已交付
O&M task
O&M backlog | new avr 1.2.3 test | 3hours | ongoing | big i3 FRR test ongoing, 100 times reboot
O&M operation record | Content | operator
xiongdi | 修改带宽为5M | TM

## W02.4
working type | Content | time | status | comments/issues
New poc | quanshi | 4h | ongoing | poc 对接，由于事先并未得知客户内网中存在多个子网，并且也需要无nat的内网通信，以致于和原本用于服务器上外网的nat设置冲突，需重新协商方案
O&M tasks | new avr test | 4h | ongoing | big i3 test，100 times interface enable/disable
O&M backlog
O&M operation record | Content | operator

## W02.5
working type | Content | time | status | comments/issues
New poc
O&M Task | new avr test | 4h | ongoing | big i3 test，FRR finished，stability ongoing
O&M backlog
O&M operation record | Content | operator